## Risk Register
Risk ID | Risk Description | Potential Impact | Likelihood (L) | Severity (S) | Risk Level (L x S) | Control Measures | Responsible Party | Action Plan | Status
RM-002 | Resource Depletion | Depletion of natural resources, supply chain disruption | Moderate | High | High | Conduct resource efficiency assessments | Sustainability Manager | Implement resource efficiency measures, track resource usage trends | In Progress
RM-003 | Pollution | Environmental contamination, regulatory fines | High | High | High | Install pollution control technologies | Environmental Health & Safety Officer | Conduct regular environmental audits, upgrade pollution control systems | Ongoing
RM-004 | Climate Change Impact | Extreme weather events, regulatory non-compliance | High | High | High | Develop climate change adaptation strategies | Climate Change Officer | Integrate climate resilience into business operations, monitor weather forecasts | Planned
Risk Rating Matrix
Risk Level | Description | Indicator
Low | Low potential impact and likelihood | Green
Moderate | Moderate potential impact and likelihood | Yellow
High | High potential impact and likelihood | Red
SAMPLE RISK REGISTER
Keys
Likelihood (L):** Assess the likelihood of the risk occurring on a scale of Low, Moderate, or High.
Severity (S):** Assess the potential impact of the risk on a scale of Low, Moderate, or High.
Risk Level (L x S):** Calculate the risk level by multiplying Likelihood and Severity.

## Opp. Register
OPPORTUNITY SUMMARY | OPPORTUNITY DESCRIPTION | OPPORTUNITY TYPE | OPPORTUNITY OWNER | LIKELIHOOD | LIKELIHOOD RATIONALE | IMPACT | IMPACT RATIONALE | OPPORTUNITY SCORE | OPPORTUNITY LEVEL | ACTION | ACTION OWNER | COMMENTS
Opp-001 | Implement Renewable Energy Sources | Sustainability Initiative | Operations Manager | High | Rising energy costs and environmental concerns | High | Reduced carbon footprint and long-term cost savings | 8 | High | Assess feasibility and ROI of integrating renewable energy | Sustainability Team | Evaluate potential suppliers and technologies.
Opp-002 | Reduce Waste Generation through Recycling | Waste Management | Environmental Officer | Moderate | Increasing regulatory pressure and public awareness | Moderate | Decreased waste disposal costs and environmental impact | 7 | High | Develop and implement a comprehensive recycling program | Waste Management Team | Conduct waste audit and identify recycling opportunities.
SAMPLE OPPORTUNITY REGISTER