## Risk Register
Risk ID | Risk Description | Potential Impact | Likelihood (L) | Severity (S) | Risk Level (L x S) | Control Measures | Responsible Party | Action Plan | Status
RM-001 | Natural Disasters | Property damage, service disruptions, loss of life | Low | High | Moderate | Develop and implement disaster preparedness plans, Regular drills and training exercises | Facilities Manager | Conduct risk assessments for natural disasters, Develop and communicate evacuation procedures, Train employees on emergency response protocols | Ongoing
RM-002 | Technology Obsolescence | Inefficient operations, compatibility issues, increased costs | Moderate | Moderate | Moderate | Stay updated on technological advancements, Implement technology refresh cycles | IT Manager | Conduct regular technology assessments, Develop a technology roadmap, Budget for technology upgrades | In Progress
RM-013 | Employee Turnover | Knowledge loss, decreased productivity, recruitment costs | Moderate | Moderate | Moderate | Implement employee retention strategies, Provide ongoing training and development | Human Resources | Conduct exit interviews, Develop employee engagement initiatives, Provide career advancement opportunities | Ongoing
Risk Rating Matrix
Risk Level | Description | Indicator
High | High potential impact and likelihood | Red
Moderate | Moderate potential impact and likelihood | Yellow
Low | Low potential impact and likelihood | Green
SAMPLE RISK REGISTER
Keys
Likelihood (L):** Assess the likelihood of the risk occurring on a scale of Low, Moderate, or High.
Severity (S):** Assess the potential impact of the risk on a scale of Low, Moderate, or High.
Risk Level (L x S):** Calculate the risk level by multiplying Likelihood and Severity.

## Opp. Register
OPPORTUNITY SUMMARY | OPPORTUNITY DESCRIPTION | OPPORTUNITY TYPE | OPPORTUNITY OWNER | LIKELIHOOD | LIKELIHOOD RATIONALE | IMPACT | IMPACT RATIONALE | OPPORTUNITY SCORE | OPPORTUNITY LEVEL | ACTION | ACTION OWNER | COMMENTS
Opp-001 | Implement Incident Management Procedures | Process Improvement | Service Delivery Manager | High | Lack of structured incident management procedures. | High | Reduced response time, improved customer satisfaction. | 8 | High | Develop and implement incident management procedures. | IT Department | Train staff and establish incident categorization process.
Opp-002 | Enhance Service Desk Capability | Technology Enhancement | Service Desk Manager | Moderate | Current service desk lacks necessary tools and resources. | High | Improved response times, enhanced user support experience. | 7 | High | Upgrade service desk software and provide additional training. | IT Department | Assess software options and schedule training sessions.
SAMPLE OPPORTUNITY REGISTER