## Risk Register
Risk ID | Risk Description | Potential Impact | Likelihood (L) | Severity (S) | Risk Level (L x S) | Control Measures | Responsible Party | Action Plan | Status
RM-001 | Fire Hazard | Property damage, injury, loss of life | High | High | High | Conduct regular fire drills and training, Install and maintain fire detection and suppression systems, Establish evacuation procedures | Facilities Manager | Review and update evacuation procedures quarterly, Ensure fire safety equipment is inspected and maintained | Ongoing
RM-002 | Utility Outages | Disruption of operations, potential data loss | Moderate | High | High | Implement backup power systems, Develop contingency plans for utility outages, Regularly test backup systems | Operations Manager | Schedule regular tests of backup power systems, Review and update contingency plans annually | In Progress
RM-003 | Security Breach | Theft, data breaches, unauthorized access | Moderate | Moderate | Moderate | Implement access control measures, Conduct security audits and vulnerability assessments, Employee training on security protocols | Security Officer | Conduct quarterly security audits, Provide regular training on security best practices | Not started
RM-004 | Equipment Failure | Disruption of services, increased maintenance costs | High | Moderate | High | Implement a preventive maintenance program, Keep spare equipment in stock, Regularly monitor equipment performance | Maintenance Supervisor | Develop a preventive maintenance schedule, Maintain a stock of critical spare parts | In Progress
Risk Rating Matrix
Risk Level | Description | Indicator
Low | Low potential impact and likelihood | Green
Moderate | Moderate potential impact and likelihood | Yellow
High | High potential impact and/or likelihood | Red
SAMPLE RISK REGISTER
Keys
Likelihood (L):** Assess the likelihood of the risk occurring on a scale of Low, Moderate, or High.
Severity (S):** Assess the potential impact of the risk on a scale of Low, Moderate, or High.
Risk Level (L x S):** Calculate the risk level by multiplying Likelihood and Severity.

## Opp. Register
OPPORTUNITY SUMMARY | OPPORTUNITY DESCRIPTION | OPPORTUNITY TYPE | OPPORTUNITY OWNER | LIKELIHOOD | LIKELIHOOD RATIONALE | IMPACT | IMPACT RATIONALE | OPPORTUNITY SCORE | OPPORTUNITY LEVEL | ACTION | ACTION OWNER | COMMENTS
Upgrade HVAC System | Replace outdated HVAC systems with energy-efficient models | Maintenance | Facitliy Manager | High | Aging equipment, rising energy costs | High | Energy savings, improved comfort | 9 | High | Procure new HVAC units | Facilities Manager | Budget approval pending
Sustainability Audit | Conduct an environmental audit to identify energy-saving opportunities | Sustainability | Sustainability Coordinator | Moderate | Limited data on current consumption | High | Reduced energy costs, environmental benefits | 7 | Moderate | Hire an audit firm | Sustainability Coordinator | RFP issued, awaiting responses
Security System Upgrade | Implement advanced security systems with access control | Security | Security Manager | Low | No recent security breaches | High | Improved safety, reduced risk | 5 | Low | Research security vendors | Security Manager | Vendor list compiled, initial inquiries made
SAMPLE OPPORTUNITY REGISTER