## Risk Register
Risk ID | Risk Description | Potential Impact | Likelihood (L) | Severity (S) | Risk Level (L x S) | Control Measures | Responsible Party | Action Plan | Status
CM-001 | Inadequate Record Security | Data breaches, unauthorized access | Moderate | High | High | Implement access controls and encryption, Conduct regular security audits | Records Manager | Review and update access controls quarterly, Schedule annual security audits | In Progress
CM-002 | Data Loss or Corruption | Loss of critical records, legal liabilities | High | Moderate | High | Implement automated data backup and recovery systems, Conduct regular data integrity checks | IT Manager | Implement automated backup and recovery systems, Conduct monthly data integrity checks | Ongoing
CM-003 | Inadequate Metadata Management | Difficulty in record retrieval, inefficiencies | Moderate | Moderate | Moderate | Implement a standardized metadata system, Train staff on metadata best practices | Records Manager | Develop and implement a metadata system, Conduct quarterly staff training | Not started
Risk Rating Matrix
Risk Level | Description | Indicator
Low | Low potential impact and likelihood | Green
Moderate | Moderate potential impact and likelihood | Yellow
High | High potential impact and/or likelihood | Red
SAMPLE RISK REGISTER
Keys
Likelihood (L):** Assess the likelihood of the risk occurring on a scale of Low, Moderate, or High.
Severity (S):** Assess the potential impact of the risk on a scale of Low, Moderate, or High.
Risk Level (L x S):** Calculate the risk level by multiplying Likelihood and Severity.

## Opp. Register
OPPORTUNITY SUMMARY | OPPORTUNITY DESCRIPTION | OPPORTUNITY TYPE | OPPORTUNITY OWNER | LIKELIHOOD | LIKELIHOOD RATIONALE | IMPACT | IMPACT RATIONALE | OPPORTUNITY SCORE | OPPORTUNITY LEVEL | ACTION | ACTION OWNER | COMMENTS
OPP-001 | Automated Compliance Reporting | Technology Enhancement | Compliance Manager | Moderate | Manual reporting processes are prone to errors and delays. | High | Improved accuracy and timeliness of compliance reporting | 7 | High | Initiate a project to implement automated compliance reporting software | IT Department | Assess budget and scope for the software implementation
OPP-002 | Standardize Compliance Training | Process Improvement | Training Coordinator | Low | Current training programs are sufficient | Medium | Enhanced consistency in compliance knowledge and practices | 5 | Medium | Review and standardize compliance training programs | Compliance Team | Identify areas of improvement and update training materials
SAMPLE OPPORTUNITY REGISTER